Lokaal

Your City. Your Campus. Your Guide.

Project Proposal, Plan of Action & Financial Projections

| Team: Shashank, Karthikeya, Ajay, Sandeep | Stage: Pre-launch / Pilot |
| --- | --- |
| Pilot City: Kanchipuram, Tamil Nadu | Document Date: May 2026 |

01 ¦ The Problem We Are Solving

## The student experience in a new college town is broken

Every year, thousands of students arrive in college towns like Kanchipuram with no local knowledge — no idea where to eat, shop, or explore, and no trusted source to find out. The problem is not a lack of information on the internet; it is a lack of curated, student-specific, locally accurate information in one accessible place.

### Three specific pain points we have experienced ourselves:

- Discovery friction — finding even a basic mess or grocery shop near campus requires asking seniors or trial-and-error. Google Maps shows options but not which ones are actually good, affordable, or student-friendly.

- The auto tax — the single biggest practical problem for students in Enathur is transport cost. A trip to Kanchipuram for groceries or stationery costs Rs. 300-400 in auto charges alone, which on a student budget is a serious recurring expense.

- No student-centric travel resource — students want affordable weekend trips from campus but have no reliable source for routes, costs, timings, and student-budget breakdowns.

Core Insight: The student is the target user. We are not outsiders trying to understand this problem — we live it every day. That is our unfair advantage.

02 ¦ The Proposal

## Lokaal — A student city platform built around four pillars

Lokaal is a web-first platform that serves as the definitive local guide and utility layer for students in any Indian college town. The platform launches in Kanchipuram as a pilot, with a clear template to expand to any college city in Tamil Nadu and beyond.

| Pillar | Section | What It Solves | Revenue Model |
| --- | --- | --- | --- |
| 01 | Food & Restaurants | Where to eat, price range, student-friendly options near campus | Featured listings, paid badges |
| 02 | Shopping Guide | Where to buy stationery, clothes, electronics, essentials in town | Featured listings, deals section |
| 03 | Places & Travel Routes | What to visit in and around Kanchipuram, weekend trip guides with student budgets | Affiliate travel bookings, sponsored routes |
| 04 | Hyperlocal Delivery | Order groceries or essentials from Enathur shops, delivered by campus riders for Rs. 40-50 vs Rs. 300-400 auto fare | Per-delivery commission (Rs. 15-20 per order) |

The delivery section is the anchor of the business model in Phase 1. It creates daily repeat usage, generates immediate transactional revenue, and serves as the most compelling proof-of-traction when approaching larger Kanchipuram businesses for listing partnerships.

03 ¦ Plan of Action

## Phase 0  —  Research & Setup  (Weeks 1-2)

Goal: Define the product, set up infrastructure, and begin ground-level content collection before writing any code.

- Register the domain and set up a landing page with a waitlist form — creates social proof before launch.

- Create a shared Google Sheet with listing fields: Name, Category, Address, Maps Link, Price Range, Photos, Tags, Insider Tip.

- Finalise the tech stack: React (frontend), Firebase Firestore (database + hosting), simple admin panel for managing listings.

- Ajay and Sandeep begin ground research — walk Kanchipuram, visit shops, photograph places, fill the Sheet with real listings.

- Identify 3-5 bike-owning students willing to do delivery runs for a commission. Have explicit WhatsApp agreement on the split.

- Test the manual delivery flow on WhatsApp — take 5 test orders, coordinate manually, measure what breaks.

## Phase 1  —  MVP Build  (Weeks 3-6)

Goal: Ship a working platform with real listings and a functional delivery ordering flow. Imperfect but live.

- Shashank builds the frontend — home page with 4 categories, listing cards with photo, description, price, maps link and tags, and mobile-first responsive layout.

- Karthikeya builds the backend — Firebase schema, admin panel to add/edit listings from the Google Sheet, deployment on Firebase Hosting.

- Delivery section MVP: simple order form (item, quantity, shop name, room number), WhatsApp notification to the assigned rider, UPI payment upfront. No complex real-time tracking needed at this stage.

- Ajay and Sandeep continue adding content — target 60 listings at launch across all four sections. Write one insider tip per listing.

- End-of-phase review: all four team members test every flow, log bugs, fix before launch.

## Phase 2  —  Launch & Early Revenue  (Weeks 7-10)

Goal: Get live, get users, get the first paying business. Use delivery revenue as proof for listing partnerships.

- Launch via college WhatsApp groups, notice board QR codes, and word of mouth. Target: 300+ unique visitors in the first two weeks.

- Run delivery service actively — even 5 orders per day at Rs. 50 each generates Rs. 7,500 per month in gross delivery revenue.

- After 30-45 days, walk into small Kanchipuram shops with: delivery transaction screenshots, platform visitor count from Google Analytics, and a clear Rs. 500/month featured listing pitch.

- Target: 3 paying businesses by end of Month 2. This is your proof of income — screenshot every UPI transfer and maintain a simple revenue log.

- Set up Google Analytics for traffic data and add a Suggest a Place form to begin community contribution.

## Phase 3  —  Scale & Deepen  (Months 3-5)

Goal: Expand to more Kanchipuram businesses, introduce student deals, and prepare the template for the next city.

- Introduce a Deals section — partner shops offer student discounts (show app = 10% off). Students return daily to access deals, not just for discovery.

- Add user reviews and community tips with moderation by Ajay and Sandeep.

- Expand the travel routes section with documented weekend trips — Mahabalipuram, Pondicherry, Tiruvannamalai, Chennai — with student budget breakdowns.

- Begin conversations with Vellore and Tiruchirappalli student networks. Identify a content team in each city using the same model (local students as researchers).

- Shashank and Karthikeya build the PWA / mobile-optimised app layer. Push notifications for new deals and delivery status updates.

## Phase 4  —  Full Commercialisation  (Month 6+)

Goal: Three revenue streams running, multi-city presence, and university partnership conversations in progress.

- Revenue stream 1: Paid featured listings across all cities — Rs. 500 to Rs. 2,000 per month per business depending on category and footfall.

- Revenue stream 2: Affiliate commissions — Swiggy and Zomato both have affiliate programs. Every order placed through a platform referral link earns a commission per transaction.

- Revenue stream 3: University tie-ups — pitch to university welcome and hostel offices to include Lokaal in fresher orientation packs. One institutional deal can be worth Rs. 10,000 to Rs. 50,000 per year.

- Begin preparing an investor-ready deck with actual revenue data, user growth curve, and the city expansion roadmap.

04 ¦ Clear-Cut Roadmap

| Timeline | Milestones & Deliverables |
| --- | --- |
| Week 1-2 (Phase 0) | Domain registered. Waitlist live. Google Sheet with listing fields shared. 3-5 delivery riders confirmed. Manual delivery tested on WhatsApp. 20+ listings collected by Ajay & Sandeep. |
| Week 3-4 (Phase 1 - Build) | Frontend skeleton live on Vercel/Firebase. Listing cards for Food and Shopping sections functional. Admin panel for adding listings working. Delivery order form live with WhatsApp notification. |
| Week 5-6 (Phase 1 - Complete) | All 4 sections live. 60+ listings published. Mobile-responsive tested on Android. Travel routes section with 3 destinations published. Full team QA pass. Platform launched. |
| Week 7-8 (Phase 2 - Launch) | Platform live. Announced in college WhatsApp groups. QR codes on campus. Delivery running. Google Analytics tracking. Target: 300+ unique visitors. |
| Week 9-10 (Phase 2 - Revenue) | 5+ daily delivery orders. 3 paying businesses signed for featured listings. Revenue log started. Visitor + revenue screenshot pack prepared for business pitch use. |
| Month 3 (Phase 3 - Expand) | Deals section live. User review system launched. 2 new travel routes published. 10+ paying businesses. Planning call with Vellore student contact for city 2. |
| Month 4-5 (Phase 3 - Scale) | PWA version live. Push notifications active. 500+ monthly active users. Community content flowing. City 2 content collection begun. Affiliate links integrated with Swiggy/Zomato. |
| Month 6+ (Phase 4 - Commercial) | 3 revenue streams active. Multi-city presence. University tie-up pitch prepared. First investor deck drafted. Monthly revenue target: Rs. 25,000+. |

05 ¦ Person-Wise Duties

All four are equal co-founders. Shashank and Karthikeya handle the technical build while Ajay and Sandeep own content, operations, and growth. Every major decision is made as a team. Ajay and Sandeep grow into their roles progressively — each phase adds one new skill, never overwhelming them with everything at once.

|  | Shashank — Co-Founder — Frontend Development & Business Development - Phase 0-1: Build the entire frontend — home page, listing cards, category pages, delivery order form. Mobile-first, Firebase-connected. - Phase 2: Lead business outreach. Walk into shops, pitch the featured listing model, close the first 3 paying clients. - Phase 3-4: Own the PWA build, design the deals section UI, prepare the investor deck and university partnership pitch. - Ongoing: UI quality control, frontend maintenance, and contribution to joint product decisions as a team. |
| --- | --- |

|  | Karthikeya — Co-Founder — Backend Development & Infrastructure - Phase 0-1: Set up Firebase Firestore schema, build the admin panel for listing management, handle deployment and hosting. - Phase 1: Implement delivery order flow — form submission, WhatsApp notification trigger, UPI integration. - Phase 2: Set up Google Analytics, run Lighthouse audits, ensure site loads fast on mobile (target score 85+). - Phase 3-4: Build PWA layer, push notifications, affiliate link integration, and multi-city database architecture. |
| --- | --- |

|  | Ajay — Co-Founder — Content & Social Media - Phase 0: Ground research — visit 20+ locations in Kanchipuram, photograph, fill the Google Sheet with real data. Own this completely. - Phase 1: Write insider tips for each listing. Begin learning how to use the admin CMS to add listings directly. - Phase 2: Own the Instagram account — post 3x per week (best food spots, travel routes, delivery features). Run campus QR code distribution. - Phase 3: Take over partner communications — follow up with paying businesses, coordinate deal offers, manage review moderation. - Phase 4: Learn to read Google Analytics dashboards and report weekly numbers to the team. |
| --- | --- |

|  | Sandeep — Co-Founder — Operations & Community - Phase 0: Ground research alongside Ajay — focus on shopping and places-to-visit sections. Document travel routes with timings and costs. - Phase 1: QA testing — go through every listing card, every button, every form and log what breaks. This is a critical role. - Phase 2: Manage delivery operations — coordinate between students placing orders and riders. First point of contact for delivery issues. - Phase 3: Community management — moderate user reviews, respond to suggestions, manage the Suggest a Place submissions. - Phase 4: Handle content for city 2 — brief the new city's research team using the same process he learned in Kanchipuram. |
| --- | --- |

06 ¦ Financial Statistics & Projections

## Startup costs (one-time)

The platform is designed to be launched with near-zero capital. All tools used are either free-tier or negligible cost.

| Item | Estimated Cost |
| --- | --- |
| Domain registration (1 year) | Rs. 800 – Rs. 1,200 |
| Firebase Hosting (free tier sufficient for Phase 1-2) | Rs. 0 |
| Design tools — Canva Pro (optional) | Rs. 500/month or free tier |
| Marketing — printed QR code stickers, campus boards | Rs. 300 – Rs. 500 |
| Miscellaneous (transport for ground research, etc.) | Rs. 500 – Rs. 1,000 |
| TOTAL ESTIMATED STARTUP COST | Rs. 1,600 – Rs. 3,200 |

## Revenue projections by phase

### Phase 2 (Months 1-2) — Delivery + Early Listings

| 5-8 Delivery orders/day at Rs. 50 avg delivery fee | Rs. 15-20 Platform cut per order rider keeps Rs. 30-35 | Rs. 2,250-4,800 Monthly delivery revenue platform share only | 3 Featured listing clients at Rs. 500/month each |
| --- | --- | --- | --- |

Phase 2 Monthly Revenue Estimate: Rs. 3,750 – Rs. 6,300 (Delivery: Rs. 2,250-4,800 + Listings: Rs. 1,500)

### Phase 3 (Months 3-5) — Scaled Delivery + More Listings + Deals

| 15-25 Delivery orders/day word of mouth growth | Rs. 6,750-15,000 Monthly delivery revenue platform cut only | 10-15 Paying listing clients Rs. 500-1,000/month avg | Rs. 13,750-30,000 Total monthly revenue combined streams |
| --- | --- | --- | --- |

### Phase 4 (Month 6+) — Full Three-Stream Revenue

| Revenue Stream | Source | Conservative (Rs.) | Optimistic (Rs.) |
| --- | --- | --- | --- |
| Delivery commissions | Rs. 15-20 per order, 25-40 orders/day | 11,250 | 24,000 |
| Featured listings | 15-25 businesses at Rs. 500-2,000/month | 7,500 | 50,000 |
| Affiliate commissions | Swiggy/Zomato referral per order | 2,000 | 8,000 |
| University tie-ups | Annual deal, amortised monthly | 4,000 | 15,000 |
| TOTAL MONTHLY |  | 24,750 | 97,000 |

12-Month Revenue Target: Rs. 25,000/month conservative — Rs. 97,000/month optimistic. Even the conservative number is a strong proof point for business partnerships and university tie-ups.

## The proof-of-income strategy

Before approaching any Kanchipuram business for a paid listing, the team will have at minimum 30-45 days of delivery transaction data. The pitch package prepared for each business meeting will contain:

- Screenshot log of UPI delivery transactions (total orders, total revenue generated)

- Google Analytics screenshot showing monthly unique visitors and session data

- A sample featured listing from a test or volunteer business to demonstrate visual quality

- Simple one-page revenue trend: Month 1 earnings vs Month 2 earnings showing growth direction

This approach eliminates the zero-income problem entirely. By the time we approach a business, we are not pitching potential — we are presenting a working product with real user activity and real money already moving through it.

Key Point for Business Partners: We are not asking you to take a risk. We are showing you a platform your potential customers are already using, and offering you the front row.

Built by students, for students.

Lokaal  —  Kanchipuram Pilot  —  2026